## Gantt Schedule
Project Schedule (Gantt)
▼ CURRENT
# | Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
1) Requirements + System Specs
1 | Define project scope & objectives (All)
2 | Research actuators & sensors (All)
3 | Select control architecture: PC + Arduino R4 (Helal)
4 | Finalize system block diagram (All)
5 | Component sourcing & ordering (Mohamed)
2) Mechanical CAD + Fabrication
6 | Base, shoulder & Elbow joint CAD (Helal)
7 | Motor mounting holes & wiring channels (Helal)
8 | CAD scaling & stress checks (Helal)
9 | 3D printing & assembly (All)
10 | Wrist joint CAD (Helal)
3) Electronics (Components/Wiring)
11 | Wiring schematic design (Mohamed)
12 | Power supply & servo power distribution (Mohamed)
13 | L293D / motor driver integration (Helal)
14 | Sensor wiring: IMU + encoder (Helal)
15 | Full system wiring & cable management (Helal)
4) Camera Vision
16 | Camera setup & calibration (Leen)
17 | OpenCV color detection pipeline (Leen)
18 | Shape detection & classification (Leen)
19 | Coordinate mapping: camera → robot frame (Leen)
20 | Auto-mode pick target selection (Leen)
5) End Effector
21 | End effector mechanism CAD (Mohamed)
22 | Pump/compressor selection & testing (Mohamed)
23 | IMU auto-levelling subsystem (Mohamed)
24 | End effector integration & test (Mohamed)
6) ROS2 / Digital Twin
25 | ROS2 workspace & node setup (Mohamed)
26 | URDF model from CAD export (Mohamed)
27 | Gazebo simulation environment (Mohamed)
28 | ROS2 ↔ Arduino serial bridge (Mohamed)
29 | Digital twin validation (All)
7) Firmware + Control
30 | Arduino serial protocol: servo commands (Helal)
32 | Manual mode: pygame keyboard/gamepad (Helal)
31 | PID control for DC base motor (Helal)
33 | Inverse kinematics implementation (Leen) |  |  |  |  | `
34 | Auto mode: vision → IK → servo pipeline (All)
35 | End-to-end control loop tuning (All)
8) Verification / Testing
36 | Individual joint range-of-motion tests (All)
37 | Pick-and-place accuracy tests (All)
38 | Full system stress & reliability test (All)
9) Demo + Report
39 | Final report writing (All)
40 | Demo preparation & rehearsal (All)
41 | Project demo & submission (All)