## Slide 1
WEEK 10
Robotic Arm
Pick & Place System
Weekly Progress Report · Mechatronics System Design 101
Leen's Group · Leen · Mohamed · Helal

## Slide 2
Week 10 — Snapshot
What we worked on this week
01
Pump & relay working
12V pump, relay module, and lithium batteries wired up and controlled via Arduino. Relay successfully activates and deactivates the pump on command.
02
ROS2 — arm in environment
CAD model now appears at correct positions in ROS2 environment. Arm joints are controllable and can be manipulated in simulation.
03
Arm assembly — stable
New screws procured — arm fits together perfectly and is structurally stable. Wheels received and ready to attach once base is complete.
04
Mobile base — laser cut
Laser cut base attempted twice — both broke. Redesigning with a simpler geometry before the third attempt.
Status
Pump / relay
Working ✓
ROS2 / RViz
Working ✓
Arm assembly
Stable ✓
Mobile base
Redesigning
End effector
In progress
Full assembly
Pending
✓ Major progress: pump + relay operational, ROS2 arm controllable in simulation, arm structurally stable.
Mechatronics System Design 101 · Leen's Group · Week 10

## Slide 3
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 10

## Slide 4
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 5
Milestones & Deliverables
Deliverable
Target
Status
This week
CAD model complete
Week 10
Complete ✓
All links modelled — arm fits and is stable
Pump & relay control
Week 10
Done ✓
12V pump activated via relay and Arduino
ROS2 / Digital twin
Week 10
Working ✓
Arm at correct positions, joints manipulable
End effector (gripper)
Week 10
In progress
3D printing gripper design in progress
Mobile base
Week 10
Redesigning
Laser cut failed twice — simpler design planned
Full assembly
Week 11
Pending
Waiting on base and end effector completion
Control complete
Week 11
On track
Gamepad + Python + CV + relay all functional
Mechatronics System Design 101 · Leen's Group · Week 10

## Slide 6
Issues, Risks & Action Items
Current issues & risks
High
Mobile base — laser cut failing
Two laser cut attempts broke. Root cause: design too complex for the material. Redesigning with simpler geometry before third attempt.
High
End effector not yet complete
Gripper being 3D printed. End effector assembly cannot be finalised until print is complete and fit is verified.
Medium
Full assembly blocked
Cannot fully assemble the system until both the mobile base and end effector are ready.
Medium
Box dimensions still unknown
Professor has not yet provided box dimensions — coordinate mapping and arm positioning cannot be fully finalised.
Action items
Redesign base — simpler geometry
All
Week 11
Third laser cut attempt
All
Week 11
Complete gripper 3D print
Mohamed
Week 11
Attach wheels once base is ready
All
Week 11
Full system assembly
All
Week 11
Request box dimensions from professor
Leen
Week 11
Mechatronics System Design 101 · Leen's Group · Week 10

## Slide 7
Individual
Updates
What each member did, what they will do, what they need.
Leen
Group Leader
Mohamed
Member
Helal
Member

## Slide 8
Leen — Group Leader · ROS2 & Simulation
Accomplished (since last report)
CAD model imported into ROS2 environment at correct joint positions
Arm joints are now manipulable in the simulation
Digital twin reflects the physical arm structure accurately
In progress
Linking ROS2 simulation to real Arduino control pipeline
Finalising coordinate mapping for auto pick-and-place
Next week plan
Connect ROS2 to Arduino for real-time joint control
Complete full auto pick-and-place pipeline
Request box dimensions from professor
ROS2 / Digital twin — where we are
Ubuntu VM
Installed & configured ✓
ROS2
Installed and running ✓
CAD import
Model at correct positions ✓
Joint control
Joints manipulable in sim ✓
Arduino link
ROS2 ↔ Arduino — in progress
Full demo
Pending full assembly
Help needed / questions
Box dimensions still needed from professor to finalise arm positioning and coordinate mapping for pick-and-place.
Mechatronics System Design 101 · Leen's Group · Week 10

## Slide 9
Mohamed — Member
Accomplished (since last report)
[ To be filled in by Mohamed ]
In progress
[ To be filled in by Mohamed ]
Next week plan
[ To be filled in by Mohamed ]
Evidence (show, don't tell)
[ To be filled in by Mohamed ]
Help needed / questions
[ To be filled in by Mohamed ]
Mechatronics System Design 101 · Leen's Group · Week 10

## Slide 10
Helal — Member · Hardware & Assembly
Accomplished (since last report)
Procured 12V pump, relay module, lithium batteries and case
Wired relay module to Arduino — pump activates and deactivates on command
Procured new screws — arm fits together and is structurally stable
Received wheels — ready to attach once base is complete
Laser cut base attempted twice — both attempts broke
In progress
Redesigning base with simpler geometry for third laser cut attempt
Next week plan
Third laser cut attempt with simplified base design
Attach wheels and DC motors to base
Begin full system assembly
Electrical system — what was bought
Pump
12V DC mini vacuum pump
Power
3× 3.7V lithium batteries in series (~11.1V)
Relay
Relay module — Arduino-controlled on/off for pump
Motors
2× DC motors + wheels for mobile base
Driver
L298D motor driver shield for DC motors
Screws
New M3 screws — arm assembly now stable
Help needed / questions
Base material and design needs to be validated before cutting again — two failed attempts. Need to confirm final dimensions and cut settings before third attempt.
Mechatronics System Design 101 · Leen's Group · Week 10

## Slide 11
Week 10
Wrap-up
✓
Pump + relay + batteries — working and controlled by Arduino
✓
ROS2 arm at correct positions in simulation — joints manipulable
✓
Arm structurally stable — new screws fit perfectly
✓
Wheels and DC motors received
⚠
Mobile base laser cut failed twice — redesigning for third attempt
⚠
End effector / gripper still being 3D printed
✗
Box dimensions still not received from professor
Looking ahead
Week 11
Simplified base — third laser cut
Week 11
Finish gripper + end effector
Week 11
Attach wheels + motors to base
Week 11
Full system assembly
Week 11
ROS2 ↔ Arduino live link
Week 11
Full pick-and-place demo
Mechatronics System Design 101 · Leen's Group · Week 10