## Slide 1
WEEK 11
Robotic Arm
Pick & Place System
Weekly Progress Report · Mechatronics System Design 101
Leen's Group · Leen · Mohamed · Helal

## Slide 2
Week 11 — Snapshot
What we worked on this week
01
Full manual control working
Gamepad now controls wheel motors, all servo joints, and the pump in a single unified control loop. Full manual operation of the system confirmed.
02
Mobile base — laser cut done
Two platforms successfully laser cut. Standoffs procured to space them apart. Base structure is coming together.
03
CAD — scale verification needed
Further progress on CAD model. Printed parts need to be measured and compared to CAD to correct any scale discrepancies.
04
Detection — retraining model
Collected more images in a crowded environment. Model will be retrained to improve detection accuracy in realistic conditions.
Status
Manual control
Working ✓
Mobile base
In progress
ROS2
In progress
CAD
Scale check
Detection
Retraining
End effector
No update
✓ Major win: full manual control of wheels, servos, and pump confirmed working from a single gamepad.
Mechatronics System Design 101 · Leen's Group · Week 11

## Slide 3
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 11

## Slide 4
Milestones & Deliverables
Deliverable
Target
Status
This week
Manual control (full)
Week 11
Done ✓
Wheels + servos + pump via gamepad — all working
Mobile base
Week 11
In progress
Two platforms laser cut — standoffs fitted
CAD model
Week 11
Scale check
Progress made — need to verify printed part dimensions
Detection model
Week 11
Retraining
More images collected — model retraining in progress
ROS2 / Digital twin
Week 11
In progress
Joint positions not yet connecting correctly
End effector
Week 11
No update
Gripper 3D print status unchanged
Full system assembly
Week 11
Pending
Waiting on base, end effector, and CAD scale fix
Mechatronics System Design 101 · Leen's Group · Week 11

## Slide 5
Issues, Risks & Action Items
Current issues & risks
High
ROS2 — joints not connecting
Worked on ROS2 this week but arm parts are not connecting at the correct positions in the simulation. Configuration still needed.
Medium
CAD scale discrepancy
Printed parts may not match CAD dimensions exactly. Need to measure and compare before adjusting the model.
Medium
End effector — no progress
Gripper 3D print has had no update. End effector assembly cannot proceed until this is resolved.
Medium
Full assembly still pending
Assembly blocked until base is complete, end effector is ready, and CAD scale is confirmed.
Action items
Fix ROS2 joint connection positions
Mohamed
Next week
Measure printed parts vs CAD — adjust
Helal
Next week
Retrain detection model
Leen
Next week
Resolve end effector / gripper
Mohamed
Next week
Complete base — attach wheels & motors
Helal
Next week
Begin full system assembly
All
Next week
Mechatronics System Design 101 · Leen's Group · Week 11

## Slide 6
Individual
Updates
What each member did, what they will do, what they need.
Leen
Group Leader
Mohamed
Member
Helal
Member

## Slide 7
Leen — Group Leader · Detection & Image Collection
Accomplished (since last report)
Collected additional training images in a crowded environment
Images captured across varied lighting and background conditions
Dataset prepared — model retraining queued
In progress
Retraining detection model on expanded crowded-environment dataset
Next week plan
Complete model retraining and evaluate accuracy
Test retrained model on live camera feed
Integrate updated detection with Arduino command pipeline
Finalise coordinate mapping once box dimensions are confirmed
Why crowded environment training?
Problem
Earlier model trained on clean backgrounds — fails when other objects or clutter are present
Solution
New images captured with multiple objects in frame — teaches model to isolate the target
Goal
Robust detection in real lab conditions regardless of surrounding clutter
Help needed / questions
Box dimensions still needed from professor — coordinate mapping for the pick-and-place sequence cannot be finalised without knowing where the boxes will be placed.
Mechatronics System Design 101 · Leen's Group · Week 11

## Slide 8
Mohamed — Member · ROS2 Integration
Accomplished (since last report)
Continued work on ROS2 — arm model loaded into simulation environment
In progress
Arm parts not yet connecting at correct positions in ROS2 — joint transforms being debugged
Next week plan
Fix joint transform positions in URDF
Verify arm model matches physical arm geometry
Begin ROS2 ↔ Arduino live control link
Resolve end effector / gripper status
ROS2 / Digital twin — current state
Ubuntu VM
Installed & running ✓
ROS2
Installed & running ✓
CAD import
Model loaded in sim ✓
Joint positions
Not connecting correctly — in progress
Arduino link
Not yet started
Full demo
Pending joint fix + assembly
Help needed / questions
URDF joint transforms are not placing parts at correct positions — need to review axis definitions and parent-child relationships in the URDF file.
Mechatronics System Design 101 · Leen's Group · Week 11

## Slide 9
Helal — Member · Control, CAD & Base
Accomplished (since last report)
Completed unified manual control code — gamepad drives wheel motors, actuates all servo joints, and activates pump simultaneously
Two base platforms successfully laser cut
Standoffs procured to space the two platforms apart
Further progress on CAD model
In progress
Measuring printed parts to check scale against CAD model
Next week plan
Adjust CAD model based on measured part dimensions
Assemble base — attach wheels and DC motors
Begin full system assembly
Manual control — what the gamepad controls
Left stick
Drive wheel motors — forward / backward / turn
Right stick
Shoulder and elbow servo joints
Triggers
Wrist servo — up/down
Buttons
Pump on/off via relay
Bumpers
Base joint rotation
All modes
Single unified Arduino firmware sketch
Help needed / questions
Printed parts may be scaled down relative to the CAD. Need to physically measure each part and update the CAD before the model can be used for final assembly planning.
Mechatronics System Design 101 · Leen's Group · Week 11

## Slide 10
Week 11
Wrap-up
✓
Full manual control — wheels, servos, and pump via single gamepad
✓
Mobile base platforms laser cut — standoffs fitted
✓
More training images collected in crowded environment
⚠
CAD scale needs verification against printed parts
⚠
ROS2 joint positions not yet connecting correctly
⚠
End effector / gripper — no update this week
Looking ahead
Next
Fix ROS2 joint transforms
Next
Retrain + test detection model
Next
Verify CAD scale + adjust
Next
Assemble base + attach wheels
Next
Resolve end effector
Next
Full system assembly + demo
Mechatronics System Design 101 · Leen's Group · Week 11