## Slide 1
WEEK 12
Robotic Arm
Pick & Place System
Weekly Progress Report · Mechatronics System Design 101
Leen's Group · Leen · Mohamed · Helal

## Slide 2
Week 12 — Snapshot
What we worked on this week
01
Detection — simplified & improved
Decided egg and ball are similar enough in size — system detects object presence rather than classifying type. Detection now more reliable and practical.
02
End effector — parts acquired
Tube, connector, and suction cup procured. Gripper still needs to be printed. One connecting part failed to print and needs to be reprinted.
03
Mobile base — fully assembled
Both platforms drilled, 4 columns fitted between them, wheels on bottom platform, hole in top platform for wire routing. Arduino seated between the two bases.
04
Pump — tested
Pump tested with the suction cup and tubing. Suction force verified on representative objects.
Status
Mobile base
Assembled ✓
Detection
Simplified ✓
Pump
Tested ✓
End effector
In progress
Gripper print
Pending
Full assembly
Near ready
✓ Major win: mobile base fully assembled — wheels, columns, wire routing, and Arduino housing all complete.
Mechatronics System Design 101 · Leen's Group · Week 12

## Slide 3
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 12

## Slide 4
Milestones & Deliverables
Deliverable
Target
Status
This week
Mobile base
Week 12
Done ✓
Drilled, columns fitted, wheels on, wire hole cut
Detection system
Week 12
Done ✓
Simplified — detects object presence reliably
Pump testing
Week 12
Done ✓
Suction confirmed working with tube and cup
End effector (suction)
Week 12
In progress
Tube, connector, cup acquired — needs connector part reprint
Gripper print
Week 12
Pending
Still needs to be printed
Full assembly
Week 12
Near ready
Blocked only by gripper and failed part reprint
Control complete
Week 12
On track
Manual control fully working — auto pending CV
Mechatronics System Design 101 · Leen's Group · Week 12

## Slide 5
Issues, Risks & Action Items
Current issues & risks
High
Failed part print — end effector
One part that connects to the end effector failed to print. Needs to be reprinted before the end effector can be fully assembled.
High
Gripper not yet printed
Gripper design still needs to be printed. End effector assembly cannot be completed until this is done.
Medium
Full assembly pending
All other components are ready — assembly is blocked only by the two missing printed parts.
Medium
ROS2 joint positions
Joint connection issue from last week not yet resolved. Integration with live control still pending.
Action items
Reprint failed end effector connector
Helal
Next week
Print gripper
Mohamed
Next week
Assemble full end effector
All
Next week
Full system assembly
All
Next week
Fix ROS2 joint transforms
Mohamed
Next week
Test full pick-and-place cycle
All
Next week
Mechatronics System Design 101 · Leen's Group · Week 12

## Slide 6
Individual
Updates
What each member did, what they will do, what they need.
Leen
Group Leader
Mohamed
Member
Helal
Member

## Slide 7
Leen — Group Leader · Detection & End Effector
Accomplished (since last report)
Improved and simplified detection system — egg and ball treated as same object category since sizes are nearly identical
System now detects object presence reliably without needing exact classification
Procured suction tube, connector, and suction cup for end effector assembly
In progress
Integrating updated detection with the full auto control pipeline
Next week plan
Complete end effector assembly once reprints arrive
Test full detection-to-command pipeline
Begin full pick-and-place cycle testing
Detection — design decision
Old approach
Classify object type (bolt, egg, ball) separately — complex and error-prone
New approach
Detect that an object is present and in range — simpler and more reliable
Justification
Egg and ball are nearly identical in size — separate classification adds unnecessary complexity
Result
Detection is now faster, more reliable, and easier to integrate with the control pipeline
End effector — parts status
Suction cup
Procured ✓
Tube
Procured ✓
Connector
Procured ✓
Connector part (3D print)
Failed — needs reprint
Gripper
Not yet printed
Mechatronics System Design 101 · Leen's Group · Week 12

## Slide 8
Mohamed — Member · Base Assembly & Pump Testing
Accomplished (since last report)
Assisted with drilling both circular base platforms
Helped assemble base structure — columns, wheels, and wire routing hole
Tested pump suction with tube and cup — confirmed working on representative objects
In progress
Gripper design — needs to be printed
Next week plan
Print gripper
Assemble full end effector
Fix ROS2 joint position issue
Begin full system assembly and testing
Pump test results
Bolt
Picked up successfully ✓
Ball
Picked up successfully ✓
Egg
Picked up successfully ✓
Seal
Cup seals on flat and curved surfaces ✓
Help needed / questions
Gripper print is the last remaining blocker for end effector completion. Once printed and assembled, full system testing can begin. ROS2 joint transform issue still needs to be resolved before digital twin can mirror real arm.
Mechatronics System Design 101 · Leen's Group · Week 12

## Slide 9
Helal — Member · Base Assembly & End Effector
Accomplished (since last report)
Drilled both circular base platforms
Fitted 4 standoff columns between the two platforms
Attached wheels to bottom platform
Cut wire routing hole in top platform
Arduino seated and secured between the two platforms
Procured suction tube, connector, and suction cup
In progress
Reprint of failed end effector connector part
Next week plan
Reprint connector part and assemble end effector
Attach wheels and DC motors to base
Begin full system assembly
Mobile base — what was built
Top platform
Circular — drilled — wire hole cut for Arduino wiring
Arduino
Seated between platforms — wires routed through top hole
Columns
4× standoffs spacing the two platforms apart
Bottom platform
Circular — drilled — wheels attached underneath
Wheels
DC motors + wheels on bottom for mobile movement
Power
Batteries and relay housed in base structure
Help needed / questions
Connector part reprint is the only remaining blocker before end effector can be assembled.
Mechatronics System Design 101 · Leen's Group · Week 12

## Slide 10
Week 12
Wrap-up
✓
Mobile base fully assembled — drilled, columns, wheels, wire routing
✓
Detection simplified — object presence detection, egg/ball treated as one
✓
Pump tested — all three objects picked up successfully
✓
End effector parts procured — tube, connector, suction cup
⚠
Connector part failed to print — needs reprinting
⚠
Gripper not yet printed — last blocker for end effector
⚠
ROS2 joint positions still not resolved
Looking ahead
Next
Reprint connector + print gripper
Next
Assemble full end effector
Next
Attach wheels + motors to base
Next
Full system assembly
Next
Fix ROS2 joint transforms
Next
Full pick-and-place demo
Mechatronics System Design 101 · Leen's Group · Week 12