## Slide 1
WEEK 4
Robotic Arm
Pick & Place System
Weekly Progress Report · Mechatronics System Design 101
March 25 – March 31, 2025
Leen's Group · Leen · Mohamed · Helal

## Slide 2
Week 4 — Snapshot
What we worked on this week
01
CAD model update
Continued refining the arm model in Autodesk Inventor. Wrist joint and end effector mount still in progress — geometry for base, shoulder, and elbow is locked.
02
OpenCV — computer vision
Started setting up the OpenCV pipeline on the PC. Color/shape-based object detection approach being prototyped — no AI training required.
03
Electrical components & code
Procured electrical components including Arduino R3, motor driver, and servo set. Began bench testing of Arduino code — basic servo PWM control verified and responding correctly.
Status
Schedule
On track
Scope
Defined
CAD
In progress
Hardware
Procured
Code
Testing
⚠ CAD wrist joint and end effector mount still require work — targeted for completion by Week 6.
Mechatronics System Design 101 · Leen's Group · Week 4

## Slide 3
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 4

## Slide 4
Milestones & Deliverables
Deliverable
Target
Status
Progress this week
CAD model complete
Week 6
In progress
Base/shoulder/elbow done. Wrist & EE mount in progress.
Camera vision (OpenCV)
Week 8
Started
Color/shape detection pipeline being prototyped on PC.
End effector
Week 9
Planned
Custom design pending CAD completion. Pump/Comp TBD.
ROS2 & digital twin
Week 10
Started
ROS2 environment set up. Gazebo simulation begun.
Full assembly
Week 10
Planned
3D printing of parts started for early fit testing.
Control system integration
Week 11
Planned
PC + Arduino R4 serial comms. Arduino code prototyped.
✓ This week: electrical components procured, 3D printing of arm parts started, Arduino code testing begun.
Mechatronics System Design 101 · Leen's Group · Week 4

## Slide 5
Issues, Risks & Actions
Current issues & risks
Medium
Suction pump undecided
Still evaluating mini compressor vs micro diaphragm pump vs venturi. Affects end effector timeline.
Medium
CAD wrist & end effector
Wrist joint and end effector mount geometry not yet finalised — blocking 3D print of those parts.
High
Team coordination
Difficulty scheduling meetings and exchanging work between members due to conflicting availability.
High
ROS2 learning curve
ROS2 and Gazebo are new to the team — early stage setup taking longer than anticipated.
Actions & mitigations
Pending
Pump selection
Test available options in lab Week 5 — select based on suction force and size fit.
In progress
CAD completion
Wrist and EE mount to be finalised by Week 6. Scale and wiring routing to follow.
In progress
Team sync
Set a fixed weekly check-in slot. Use shared drive for exchanging files between members.
In progress
ROS2 ramp-up
Team to follow ROS2 + Gazebo tutorials in parallel. Simple URDF model targeted for Week 6.
Mechatronics System Design 101 · Leen's Group · Week 4

## Slide 6
Individual
Updates
What each member did, what they will do, what they need.
Leen
Group Leader
Mohamed
Member
Helal
Member

## Slide 7
Leen — Group Leader · Vision & Detection
Accomplished (since last report)
Secured and confirmed the camera to be used for the project
Researched OpenCV vs YOLOv4 for object detection
Decided on OpenCV color/shape detection — no training needed, better fit for controlled lab environment
In progress
Setting up OpenCV detection pipeline on PC with connected camera
Next week plan
Begin implementing OpenCV detection script on PC
Test camera feed and object detection on sample items
Integrate detection output with serial command pipeline
OpenCV vs YOLOv4 — decision rationale
OpenCV ✓
No training required
Works with controlled lighting
Simpler to implement & debug
YOLOv4 ✗
Requires training data & GPU
Overkill for a fixed lab setup
Help needed / questions
No blockers this week. Camera secured and detection approach confirmed — ready to begin coding pipeline.
Mechatronics System Design 101 · Leen's Group · Week 4

## Slide 8
Leen — Group Leader · Vision & Detection
Mechatronics System Design 101 · Leen's Group · Week 4

## Slide 9
Mohamed — Member
Components Purchased
4× MG996R Servo Motors
L293D Motor Shield (H-Bridge)
400mm Male-Male Jumper Wires
Arduino Code
2-DOF serial servo controller
Base & Shoulder joints (pins 9 & 10)
Serial command parsing
Input validation & status query
Week 4 • Mohamed • Robotic Arm Project

## Slide 10
Mohamed — Member
Week 4 • Mohamed • Robotic Arm Project

## Slide 11
Mohamed — Member
Components Purchased
MG996R Servo Motors ×4
Actuates the shoulder, elbow, wrist, and gripper joints
Torque: 9.4 kg·cm (4.8V) / 11 kg·cm (6V)
Speed: 0.17 s/60° at 4.8V
Angle range: 0°–180°
Protocol: PWM signal
L293D Motor Shield
Interfaces servos and DC motor with the Arduino R4
Dual H-Bridge driver (L293D chip)
Servo headers on pins 9 & 10
Supports up to 4 DC motors
Direct stacking on Arduino
400mm Jumper Wires (M-M)
Internal wiring between components on the arm
Length: 400 mm
Type: Male-to-Male
Flexible routing for arm assembly
Week 4 • Mohamed • Robotic Arm Project

## Slide 12
Mohamed — Member
Arduino Code — 2-DOF Servo Controller
Arduino Sketch
#include <Servo.h>
Servo baseServo, shoulderServo;
void setup() {
Serial.begin(9600);
baseServo.attach(9);
shoulderServo.attach(10);
}
void loop() {
// Parse serial command
// Format: <servo> <angle>
// e.g. 2 45
Serial Command Parsing
Accepts '<servo> <angle>' via USB serial from PC
Input Validation
Rejects invalid servo IDs and out-of-range angles (0–180°)
Status Query
Type 'status' to print current angles of both joints
L293D Shield
Servo headers on pins 9 (Base) & 10 (Shoulder)
Week 4 • Mohamed • Robotic Arm Project

## Slide 13
Mohamed — Member
Next Steps
Expand Arduino code to control all 4 MG996R servo joints
Integrate base DC gearmotor (JGA25-370) with PID control loop
Develop Python serial interface on PC to send commands
Test serial communication between PC (Python) and Arduino R4
Begin physical assembly of servo joints on the arm structure
Mechatronics System Design • Week 4 • Mohamed

## Slide 14
Helal — Member · CAD & 3D Printing
Accomplished (since last report)
Scaled up part dimensions for better structural fit
Added motor mounting screw holes and alignment fittings
Designed internal wiring paths and cable channels
Began 3D printing of completed parts for fit testing
In progress
3D printing of arm link parts — ongoing as parts clear review
Next week plan
Complete wrist joint CAD model
Begin end effector CAD design
Evidence (show, don't tell)
Help needed / questions
Finalising suction cup mount dimensions depends on pump selection — need pump decision to complete end effector CAD.
Mechatronics System Design 101 · Leen's Group · Week 4

## Slide 15
Week 4
Wrap-up
✓
Camera secured — vision hardware confirmed
✓
Detection approach decided: OpenCV, no AI training
✓
Electrical components procured, Arduino code tested
✓
CAD updated — parts scaled, motor mounts & wiring channels added
⏳
CAD wrist joint & end effector still in progress (target Week 6)
⏳
Suction pump selection still pending
Looking ahead
Week 5
OpenCV pipeline + serial integration
Week 5
Pump testing & selection
Week 6
CAD fully complete
Week 8
Camera vision system complete
Week 9
End effector complete
Week 10
Assembly + digital twin (Gazebo)
Mechatronics System Design 101 · Leen's Group · Week 4