## Slide 1
WEEK 5
Robotic Arm
Pick & Place System
Weekly Progress Report · Mechatronics System Design 101
April 1 – April 7, 2025
Leen's Group · Leen · Mohamed · Helal

## Slide 2
Week 5 — Snapshot
What we worked on this week
01
OpenCV — data collection
Began gathering image data for the objects to be picked up. Camera connected and capture pipeline initiated.
02
End effector design
Conducted suction force calculations for cup sizing. Explored alternative gripper concepts alongside the suction cup approach.
03
Manual motor control
Diagnosed incorrect motors (continuous rotation), sourced correct servos, then implemented full gamepad control via Firmata + Processing libraries.
Status
Schedule
Behind
CAD
No progress
OpenCV
In progress
End effector
Started
ROS2
Not started
⚠ CAD made no progress this week — now targeting Week 7. ROS2 has not been started — critically behind schedule.
Mechatronics System Design 101 · Leen's Group · Week 5

## Slide 3
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 5

## Slide 4
Milestones & Deliverables
Deliverable
Target
Status
This week
CAD model complete
Week 7
Behind
No progress this week — 1 week delay
Camera vision (OpenCV)
Week 8
In progress
Collecting image data for detection
End effector design
Week 8
Started
Suction calculations done, alternatives reviewed
Manual motor control
Week 5
Done ✓
Gamepad control via Firmata + Processing working
ROS2 / Digital twin
Week 10
Not started
Critically behind — must begin Week 6
Full assembly
Week 10
Planned
3D printed parts ready, campus access needed
Control system complete
Week 11
Planned
PC + Arduino R4 pipeline being built
Mechatronics System Design 101 · Leen's Group · Week 5

## Slide 5
Issues, Risks & Action Items
Current issues & risks
High
CAD — no progress this week
Wrist joint and end effector mount remain incomplete. Now targeting Week 7 instead of Week 6.
High
ROS2 — not started
No work begun on ROS2 or Gazebo digital twin. Critically behind — required deliverable.
Medium
Campus access blocked
Finished 3D printed parts cannot be collected — team unable to get on campus this week.
Low
Team coordination difficulty
Ongoing difficulty scheduling meetings and exchanging files between members.
Action items
Begin ROS2 + Gazebo setup immediately
All members
Week 6
Resume CAD — complete wrist joint
Helal
Week 6
Arrange campus visit to collect 3D parts
Leen
Week 6
Continue OpenCV data collection
Leen
Week 6
Finalise end effector calculations
Mohamed
Week 6
Set up fixed weekly team sync
Leen
Ongoing
Mechatronics System Design 101 · Leen's Group · Week 5

## Slide 6
Individual
Updates
What each member did, what they will do, what they need.
Leen
Group Leader
Mohamed
Member
Helal
Member

## Slide 7
Leen — Group Leader
Accomplished (since last report)
Installed and configured Python and VS Code
✅ Installed Ultralytics and OpenCV libraries
✅ Wrote and tested the camera capture script
✅ Confirmed Logitech camera connection working at index 1
✅ Coordinated with team on OpenCV data collection setup
In progress
Continuing OpenCV data collection for training dataset
Preparing dataset upload and annotation on Roboflow
Next week plan
🔹 Step 3 — Upload and annotate photos on Roboflow
🔹 Step 4 — Train YOLOv8 model on Google Colab
🔹 Step 5 — Run live object detection using the camera feed
Evidence (show, don't tell)
Will Be Shown
Help needed / questions
-
Mechatronics System Design 101 · Leen's Group · Week 5
In Progress

## Slide 8
Mohamed — Member
Accomplished (since last report)
[ To be filled in by Mohamed ]
In progress
[ To be filled in by Mohamed ]
Next week plan
[ To be filled in by Mohamed ]
Evidence (show, don't tell)
[ To be filled in by Mohamed ]
Help needed / questions
[ To be filled in by Mohamed ]
Mechatronics System Design 101 · Leen's Group · Week 5

## Slide 9
Helal — Member · Motor Control & Arduino
Accomplished (since last report)
Investigated how to control servos via Arduino + gamepad controller
Wrote and tested initial Arduino code — confirmed working with controller
Identified that motors supplied were continuous rotation (incorrect type)
Returned incorrect motors and sourced correct positional servos
Implemented full servo control using Firmata protocol in Arduino IDE
Next week plan
Resume CAD — complete wrist joint model
Begin end effector CAD design
Refine control mapping between gamepad axes and joint angles
Technical implementation
Protocol
Standard Firmata (Arduino IDE)
Software
Processing IDE
Libraries
G4P + GameControlPlus
Controller
Bluetooth gamepad via PC USB
Result
Each motor controllable independently via gamepad axes
Issue resolved — wrong motors
Initial motors were continuous rotation type — no position control possible. Identified, returned, and replaced with correct positional servos on Apr 6.
CAD stalled this week — needs to resume Week 6 to meet Week 7 target.
Mechatronics System Design 101 · Leen's Group · Week 5

## Slide 10
Demo
Motor Control via Gamepad
Helal — Week 5 · Firmata + Processing + GameControlPlus
▶
[ Insert video here ]
To insert video in PowerPoint:
Insert tab
→ Video
→ This Device
Select your file
Mechatronics System Design 101 · Leen's Group · Week 5

## Slide 11
Week 5
Wrap-up
✓
Gamepad motor control working — correct servos sourced and tested
✓
OpenCV data collection started — image pipeline connected
✓
End effector suction calculations done, alternatives explored
⚠
CAD — no progress this week, now targeting Week 7
✗
ROS2 — not started, critically behind schedule
⚠
3D printed parts ready but not accessible — campus visit needed
Looking ahead
Week 6
Start ROS2 + Gazebo
Week 6
Resume CAD — wrist joint
Week 6
Collect 3D printed parts
Week 6
OpenCV detection coding begins
Week 7
CAD fully complete
Week 8
Vision + end effector complete
Mechatronics System Design 101 · Leen's Group · Week 5