## Slide 1
WEEK 7
Robotic Arm
Pick & Place System
Weekly Progress Report · Mechatronics System Design 101
Leen's Group · Leen · Mohamed · Helal

## Slide 2
Week 7 — Snapshot
What we worked on this week
01
In-person meetup + 3D parts collected & fixed
First in-person session. Collected long-delayed 3D printed parts. Servo motor fittings were wrong dimensions — team manually cut and corrected the parts on the spot.
02
OpenCV — mapping progress
Through trial and error, camera vision now detects if an object is to the left or right and sends movement commands to the Arduino base motor accordingly.
03
ROS2 installed and running
After significant learning on the new Linux OS, ROS2 is now installed and operational on the Ubuntu system — ready to begin integration work.
Status
Schedule
Recovering
3D parts
Fixed ✓
OpenCV
Progressing
ROS2
Running ✓
Assembly
Pending
CAD
On track
✓ Major win: team met in person, collected 3D parts, and corrected servo fittings on the day — assembly is now unblocked.
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 3
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 4
Milestones & Deliverables
Deliverable
Target
Status
This week
CAD model complete
Week 7
Nearly done
Parts corrected — final CAD to finish this week
New part prints
Week 8
Ordered
Corrected dimensions sent for reprint
Camera vision (OpenCV)
Week 8
Progressing
Left/right detection + base motor commands working
End effector + pump
Week 8
In progress
Pump being sourced this week
Control system
Week 8
On track
Gamepad + Python + CV commands all functional
ROS2 / Digital twin
Week 10
Running ✓
ROS2 installed and operational on Ubuntu
Full assembly
Week 10
Unblocked
Parts in hand — assembly begins once reprints arrive
Control system complete
Week 11
On track
CV pipeline sending commands to Arduino
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 5
Issues, Risks & Action Items
Current issues & risks
Resolved
Servo fittings — wrong dimensions
3D printed motor mounts did not fit. Team manually cut parts to correct on the day — new accurate parts sent for reprint.
Medium
OpenCV mapping incomplete
Left/right detection working but full coordinate mapping to arm workspace not yet done — auto pick-and-place still pending.
Medium
Assembly not yet tested
Physical assembly could not be completed this week due to fitting issues. Unblocked now — to proceed when reprints arrive.
Low
ROS2 integration not started
ROS2 is installed and running. Integration with arm control pipeline yet to begin — must start Week 8.
Action items
Complete CAD model
Helal
Week 7
Source and buy suction pump
Mohamed
Week 8
Finish OpenCV coordinate mapping
Leen
Week 8
Begin ROS2 arm integration
All
Week 8
Assemble arm once reprints arrive
All
Week 8
Test full control pipeline end-to-end
All
Week 8
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 6
Individual
Updates
What each member did, what they will do, what they need.
Leen
Group Leader
Mohamed
Member
Helal
Member

## Slide 7
Leen — Group Leader · OpenCV & Arduino Control
Accomplished (since last report)
Integrated OpenCV detection with Arduino motor control
Object detected on left → base motor turns left until centred
Object detected on right → base motor turns right until centred
Closed-loop centering behaviour confirmed working
In progress
Camera producing too many false detections — collecting more training data
Full x/y coordinate mapping to arm workspace
Next week plan
Gather and annotate more training data for camera
Improve detection accuracy — reduce false positives
Complete full coordinate mapping for auto pick-and-place
Control loop — how it works
1
Camera captures frame
OpenCV processes live video feed
2
Object position detected
Bounding box centre compared to frame centre
3
Left / right decision
If object is left → turn left. If right → turn right.
4
Command sent to Arduino
Serial command adjusts base servo until object is centred
Current issue — false detections
The camera is detecting too many incorrect objects. This is a training data problem — the model has not seen enough examples to reliably distinguish the target objects from the background and other items. More labelled images need to be collected and the model retrained before the system can be used reliably for auto pick-and-place.
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 8
Demo
OpenCV — Object Detection
Leen — Week 7 · Left/right detection sending base motor commands to Arduino
▶
[ Insert video here ]
To insert video:
Insert tab
→ Video
→ This Device
Select file
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 9
3D Printed Part Adjustments
Mohamed • Hardware & Firmware
3D Printed Arm Link
Dremel Adjustment in Lab
Parts Adjusted
Base and shoulder 3D printed links were too tight for the servo motor shaft and required post-processing.
Method – Dremel
A Dremel rotary tool was used in the lab to widen the mounting holes and clean up the tight printed tolerances.
✅ Parts Fixed
Both parts are now fully adjusted and seat correctly on the servo shafts — no reprinting required.

## Slide 10
End Effector CAD – Hybrid Design
Hybrid mechanism: vacuum suction cup + gear-driven mechanical claws. Suction cup hole diameter TBD pending servo motor fitment confirmation.
Claw Mechanism
Housing – Side View
Housing – Front Port View
🦾 Gear-Driven Claws
Two symmetrical claws actuated by a gear mechanism grip the object securely from the sides.
💨 Suction Cup Port
Hole diameter TBD — pending servo motor fitment confirmation in next CAD revision.
🔩 Material & Mounting
3D printed PLA/PETG. Housing mounts directly onto the wrist joint of the arm.

## Slide 11
Vacuum Pump – Market Research
Visited Besomi Electronics and a local electrical shop. Also searched online. Key challenge: most pumps do not list port diameter — critical for suction force calculation (F = P × A). Research ongoing.
1
Gikfun Mini DC 6V–12V R385 Diaphragm Pump
Amazon.ae • AED 36
Only option found with port dimensions clearly listed. Port ID of 5 mm gives a contact area of 19.6 mm², sufficient to lift the target objects at the compressor's operating vacuum.
2
370 Mini Vacuum Pump
DFRobot / Local • AED 26.20
Cheapest option available. Port specs are not provided — physical measurement would be required before confirming suitability for the required suction force.
3
Vacuum Pump – 12V
SparkFun / Local • AED 86.24
Most reputable brand with known reliability. Port specs unavailable online. Highest price and long lead time make this less practical for the current project timeline.

## Slide 12
Pump Options – Specification Comparison
Pump | Voltage | Port ID | Contact Area | Price (AED) | Availability | Port Specs Listed?
Gikfun R385 (Amazon.ae) | 6–12V DC | 5 mm | 19.6 mm² | 36 | In stock | ✓ Yes
370 Mini Pump (DFRobot) | TBC | Not listed | Unknown | 26.20 | In stock | ✗ No
SparkFun 12V (Local) | 12V DC | Not listed | Unknown | 86.24 | 2–3 weeks | ✗ No
Suction Force Estimate – Gikfun R385 (only option with known Port ID)
F = P × A → Port ID = 5 mm → A = π/4 × (0.005)² = 19.6 mm² | At 70 kPa: F = 70,000 × 0.0000196 ≈ 1.37 N (~140 g) ✓ Sufficient for target objects.

## Slide 13
Next Steps – Week 8
01
🔍 Continue Pump Research
Visit more suppliers and search online for pumps with port specs listed. Finalise pump selection before procurement.
02
📐 Finalise Suction Port Size
Confirm servo motor fit in CAD and determine suction cup hole diameter for the end effector housing.
03
🖨️ Begin Printing End Effector
Start 3D printing the end effector housing and claw components once suction port diameter is confirmed in CAD.
04
🔩 Full Arm Assembly
Assemble all joints with servos and test full range of motion across all 4 DOF before system integration.
PickMasters | MEC 483 – Spring 2026 | Abu Dhabi University

## Slide 14
Helal — Member · ROS2, Linux & CAD
Accomplished (since last report)
Attended in-person session — collected 3D printed parts
Helped identify and manually correct servo motor fitting dimensions on the day
Learned Linux OS fundamentals to support ROS2 workflow
Installed ROS2 successfully on Ubuntu virtual machine
Progressed through ROS2 setup — reached RViz configuration stage
In progress
RViz setup and arm model visualisation — continuing next week
Next week plan
Complete RViz arm model setup
Begin ROS2 joint control integration
Finalise CAD model — wrist & end effector
ROS2 setup — where we are
Ubuntu VM
Installed & configured ✓
ROS2
Installed and running ✓
RViz
Reached — setup in progress
URDF model
Arm model — not yet started
Joint control
ROS2 ↔ Arduino — not yet started
Help needed / questions
Linux and ROS2 are new tools — steep learning curve is slowing progress. More time needed on RViz and URDF modelling before arm integration can begin.
Mechatronics System Design 101 · Leen's Group · Week 7

## Slide 15
Week 7
Wrap-up
✓
First in-person session — team collaboration working
✓
3D parts collected and servo fittings corrected on the day
✓
OpenCV: left/right detection sending base motor commands
✓
ROS2 installed and running on Ubuntu
⚠
Full coordinate mapping not yet done — auto pipeline pending
⚠
Assembly awaiting corrected reprint parts
Looking ahead
Week 7
Finalise CAD model
Week 8
Corrected reprints arrive
Week 8
Full OpenCV coordinate mapping
Week 8
Buy pump + begin end effector build
Week 8
Begin ROS2 arm integration
Week 10
Full assembly + Gazebo digital twin
Mechatronics System Design 101 · Leen's Group · Week 7