## Slide 1
WEEK 8
Robotic Arm
Pick & Place System
Weekly Progress Report · Mechatronics System Design 101
Leen's Group · Leen · Mohamed · Helal

## Slide 2
Week 8 — Snapshot
What we worked on this week
01
CAD — wrist & base designed
Wrist link and base modelled in Autodesk Inventor. CAD model still in progress — joints not yet animating.
02
RViz — joints imported
CAD model imported into RViz. Joints are visible in simulation but not yet moving — next step is URDF joint configuration.
03
Detection improved
Switched to higher resolution images and adjusted HSV thresholds — false detection rate reduced significantly.
04
Suction pump ordered
370 mini vacuum pump selected and ordered — awaiting delivery for end effector assembly.
Status
CAD
In progress
RViz / ROS2
Imported
Detection
Improved ✓
Pump
Ordered
End effector
Behind
Assembly
Blocked
Mechatronics System Design 101 · Leen's Group · Week 8

## Slide 3
Project Schedule — Gantt Chart
[ Paste Gantt Chart Image Here ]
Mechatronics System Design 101 · Leen's Group · Week 8

## Slide 4
Milestones & Deliverables
Deliverable
Target
Status
This week
CAD model complete
Week 8
In progress
Wrist & base modelled — CAD still not finalised
Camera vision (OpenCV)
Week 8
Improved ✓
Higher res + threshold tuning — detection better
End effector + pump
Week 8
Behind
Pump ordered — end effector build pending delivery
Control system
Week 8
On track
Gamepad + Python + CV commands all functional
ROS2 / Digital twin
Week 10
In progress
Joints imported to RViz — motion not yet configured
Full assembly
Week 10
Blocked
Waiting on final 3D prints and pump delivery
Control complete
Week 11
On track
Pipeline nearly complete pending CV mapping
Mechatronics System Design 101 · Leen's Group · Week 8

## Slide 5
Issues, Risks & Action Items
Current issues & risks
High
Box dimensions unknown
Team needs box dimensions from professor before finalising wrist length and arm positioning for pick-and-place.
High
CAD & end effector behind
CAD model not yet complete and end effector cannot be built until pump arrives. Both now targeting Week 9.
Medium
RViz joints not moving
CAD imported successfully but URDF joint configuration not yet done — arm not yet animating in simulation.
Medium
Last parts not yet printed
Remaining 3D printed parts still outstanding — assembly cannot proceed until all parts are in hand.
Action items
Request box dimensions from professor
Leen
Week 9
Print remaining arm parts
Helal
Week 9
Finalise CAD model
Helal
Week 9
Configure URDF joints in RViz
Helal
Week 9
Assemble end effector once pump arrives
Mohamed
Week 9
Complete OpenCV coordinate mapping
Leen
Week 9
Mechatronics System Design 101 · Leen's Group · Week 8

## Slide 6
Individual
Updates
What each member did, what they will do, what they need.
Leen
Group Leader
Mohamed
Member
Helal
Member

## Slide 7
Leen — Group Leader · Detection Improvement
Accomplished (since last report)
Switched to higher resolution images for better detection quality
Tuned HSV colour thresholds to reduce false positives
Detection accuracy noticeably improved — fewer incorrect detections
In progress
Full x/y coordinate mapping to arm workspace
Further detection refinement for all 3 object types
Next week plan
Complete coordinate mapping for full auto control
Request box dimensions from professor
Continue refining detection for all object types
What changed — detection improvements
Image resolution
Increased → more detail per frame → better contour detection
HSV thresholds
Manually tuned lower/upper bounds → fewer false colour matches
Result
False detection rate reduced — system more reliable in lab conditions
Help needed / questions
Box dimensions are needed from the professor to finalise the coordinate mapping and arm positioning. Without knowing the box size and placement, the pick-and-place logic cannot be fully programmed.
Mechatronics System Design 101 · Leen's Group · Week 8

## Slide 8
Mohamed — Member · End Effector & Pump
Accomplished (since last report)
Selected and ordered the 370 mini vacuum pump for the end effector
In progress
Awaiting pump delivery — end effector assembly ready to begin once it arrives
Next week plan
Receive pump and begin end effector assembly
Test suction force on representative objects
Integrate pump control into Arduino firmware
370 Mini Vacuum Pump — specs
Model
370 DC mini vacuum pump
Voltage
DC 6V – 12V
Application
Suction cup end effector
Control
On/off via Arduino digital pin + relay
Status
Ordered — awaiting delivery
Help needed / questions
End effector assembly and testing is fully dependent on pump arrival. Once received, suction force will be tested against all three object types (bolt, compass, ball) to confirm it can pick each one reliably.
Mechatronics System Design 101 · Leen's Group · Week 8

## Slide 9
Helal — Member · CAD & RViz
Accomplished (since last report)
Designed wrist link CAD model in Autodesk Inventor
Updated base CAD design
Imported full CAD model into RViz — arm visible in simulation
In progress
CAD model not yet fully complete
URDF joint configuration — joints imported but not yet moving in RViz
Next week plan
Complete and finalise full CAD model
Configure URDF joint limits and axes in RViz
Begin joint motion testing in simulation
Print remaining arm parts
RViz / ROS2 — where we are
Ubuntu VM
Installed & configured ✓
ROS2
Installed and running ✓
CAD import
Model visible in RViz ✓
URDF joints
Imported — not yet moving
Joint motion
Not yet configured
Arduino link
ROS2 ↔ Arduino — not yet started
Help needed / questions
Box dimensions from professor needed to finalise wrist length in CAD. URDF joint configuration is a new area — may need additional learning time before joints animate correctly.
Mechatronics System Design 101 · Leen's Group · Week 8

## Slide 10
Week 8
Wrap-up
✓
Detection improved — higher res + threshold tuning
✓
CAD model imported and visible in RViz
✓
Wrist and base CAD designed
✓
370 mini vacuum pump ordered
⚠
CAD and end effector both behind — now targeting Week 9
⚠
RViz joints not yet moving — URDF config needed
✗
Box dimensions still needed from professor
Looking ahead
Week 9
Finalise CAD + print last parts
Week 9
Receive pump + build end effector
Week 9
Configure RViz joint motion
Week 9
Complete CV coordinate mapping
Week 9
Get box dimensions from professor
Week 10
Full assembly + Gazebo digital twin
Mechatronics System Design 101 · Leen's Group · Week 8